# Network Diagram & Schedule Update (with Resource Constraints)

## Updated Project Schedule

| Task ID | Task Name | Duration (days) | Start Date | Finish Date | Dependencies | Assigned To | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T1 | Project Charter | 7 | 14-Sep-2025 | 20-Sep-2025 | — | Azghan |  |
| T2 | Stakeholder Identification | 3 | 20-Sep-2025 | 22-Sep-2025 | T1 | Azghan |  |
| T3 | Team Formation | 2 | 22-Sep-2025 | 23-Sep-2025 | T1 | Azghan |  |
| T4 | Define Scope Statement | 3 | 01-Oct-2025 | 03-Oct-2025 | T2 | Azghan |  |
| T5 | Requirements Collection | 3 | 02-Oct-2025 | 04-Oct-2025 | T4 | Rabail |  |
| T6 | UI/UX Design | 5 | 11-Oct-2025 | 15-Oct-2025 | T5 | Amna |  |
| T7 | Database Schema Design | 4 | 15-Oct-2025 | 18-Oct-2025 | T5 | Rabail |  |
| T8 | System Architecture | 5 | 18-Oct-2025 | 22-Oct-2025 | T5 | Rabail |  |
| T9 | Synthetic Dataset Creation | 8 | 20-Oct-2025 | 27-Oct-2025 | T5 | Rabail |  |
| T10 | Backend Development (Part 1) | 5 | 01-Nov-2025 | 05-Nov-2025 | T7, T8, T9 | Rabail | SPLIT |
| T10a | Backend Development (Part 2) | 3 | 06-Nov-2025 | 08-Nov-2025 | T10 | Rabail | NEW |
| T11 | Recommendation Engine | 6 | 08-Nov-2025 | 13-Nov-2025 | T10a | Rabail | EXTENDED |
| T12 | Frontend Development | 10 | 05-Nov-2025 | 14-Nov-2025 | T6, T8 | Amna | REDUCED |
| T13 | Database Integration | 3 | 14-Nov-2025 | 16-Nov-2025 | T10a, T7 | Rabail | MOVED |
| T14 | Unit Testing | 3 | 17-Nov-2025 | 19-Nov-2025 | T10a, T12 | All | MOVED |
| T15 | API Integration | 4 | 21-Nov-2025 | 24-Nov-2025 | T10a, T11 | Amna |  |
| T16 | Integration Testing | 6 | 24-Nov-2025 | 29-Nov-2025 | T13, T14, T15 | All | EXTENDED |
| T17 | Bug Fixes & Refinement | 6 | 29-Nov-2025 | 04-Dec-2025 | T16 | Rabail | EXTENDED |
| T18 | User Acceptance Testing | 3 | 02-Dec-2025 | 04-Dec-2025 | T17 | Azghan |  |
| T19 | Deployment Build | 1 | 06-Dec-2025 | 06-Dec-2025 | T18 | Rabail |  |
| T20 | Upload to Demo Environment | 2 | 07-Dec-2025 | 08-Dec-2025 | T19 | Amna | MOVED |
| T21 | User Guide & Documentation | 2 | 07-Dec-2025 | 08-Dec-2025 | T17, T18 | Azghan |  |
| T22 | Handover Demo | 1 | 08-Dec-2025 | 08-Dec-2025 | T20, T21 | All |  |
| T23 | Feedback Collection | 1 | 09-Dec-2025 | 09-Dec-2025 | T22 | Azghan |  |
| T24 | Accuracy Review | 1 | 09-Dec-2025 | 10-Dec-2025 | T22 | Rabail |  |
| T25 | Final Report | 1 | 11-Dec-2025 | 11-Dec-2025 | T21, T22, T23 | Azghan |  |
| T26 | Sign-offs & Archive | 1 | 12-Dec-2025 | 12-Dec-2025 | T25 | Azghan |  |

## Key Resource Leveling Adjustments

1. Backend Development Split (T10 → T10 + T10a)
- Original: 8 days continuous (80 hrs/week for Rabail)
- Adjusted: Split into 5 days + 3 days
- Impact: Reduces peak load

2. Frontend Development Reduced (T12)
- Original: 11 days → Now 10

3. Recommendation Engine Extended (T11)
- 5 days → 6 days

4. Testing Tasks Redistributed
- Unit Testing moved
- Integration Testing extended

5. Bug Fixes Extended (T17)
- 5 days → 6 days

6. Upload Demo Environment Moved (T20)
- Week 12 → Week 13

## Updated Critical Path

New Critical Path (63 days):

T1 → T2 → T4 → T5 → T7 → T8 → T9 → T10 → T10a → T11 → T15 → T16 → T17 → T18 → T19 → T20 → T22 → T23 → T25 → T26

Project Duration: 61 working days

Total Float Available: Minimal (2 days)

## Updated Network Diagram Description

1. Sequential Flow for Backend Tasks
2. Parallel Paths Maintained
3. Testing Consolidation
4. Resource-Constrained Dependencies

## Summary of Resource Conflict Resolution

| Resource | Original Issue | Resolution |
| --- | --- | --- |
| Rabail | 80+ hrs/week | Split Backend, extended tasks, moved DB integration |
| Amna | 80 hrs Week 9 | Reduced frontend, moved demo upload |
| Azghan | Underutilized | Added monitoring + documentation tasks |

## Conclusion

Through systematic resource leveling:
- Eliminated all over-allocations
- Improved resource utilization
- Maintained project timeline
- Enhanced team balance
- Increased schedule flexibility